## Coding
MainALR | CODING: ALR
Coding
| Must Have |  |  |  | Want |  |  |  | Wish
DO NOT EDIT: | Status | Code | Naming Convention | Information | Status | Code | Naming Convention | Information | Status | Code | Naming Convention | Information
Do not add/remove anything! | Finished | Camera System | Node Name: Change Scene | To use the change scene node to switch to another camera, to get a location, set up the BP_CameraLocator in the right direction/location, then get the transform data and input it into a new row in the D_Scene data table, be sure to name the table and input the number correctly into the node, for node settings, input the row number and then have the dropdown on Non-Level-Fade for changing scenes inside of a level, and then Transparent to Black if you're changing into a new level (DO NOT PUT IT ON BLACK TO TRANSPARENT!!!!) If you're putting it on Transparent to Black, make sure to set the new level's name in the Data Table (D_Scenes)
Please only change objective | Finished | Scene Starter | BP_SceneStarter | Level Design Toolkit: This object is put in the level to let the handler know which camera it is supposed to start with and what scene it is supposed to play first. Make sure to NOT TOUCH THE FADE FOR THIS, DO NOT.
status and nothing else! | Finished | Dialogue Backend | Node Name: Start/Run/End Dialogue | These 3 nodes can be used to enter/bring up the ui, start a dialogue scrolling by grabbing a certain dialogue row from the data table, and the nending dialogue
| Finished | Cinematic Camera System | Node Name: Sweep Scene | To use the sweep scene node to sweep the camera between two locations, put in the first, and current location, in the Scene #1 Slot. It is very important that the camera is already at the first location you input. Next you input the desired location to interpolate to in the Scene #2 Slot, you'll have to tinker a little bit with the speed and rotate value, the rotate value should probably be VERY low though, the default values are about what is good for most cases.
| Blocked | Intro Credits | UI_Credits | (FIRST SCENE MUST BE DONE) Introduction credits to pop up during the introduction scenes as we get different views of Carl walking through the desert to El Puente, those scenes must be finished so I can get all the timing right
| Finished | Saving Player Data | Node Name: Save Data | This node saves all of the player data needed to start the game back where the player left off, the listed duration counter adds a artificial delay to the save
| Finished | Grabbing Player Data | Node Name: Grab Data | This node loads in all critical save data needed for the player to noad their saved game, the direction add a artificial delay to the load depending on what is needed in each situation
| Finished | Wipe Player Data | Node Name: Wipe Data | This node wipes all of the player's data and returns them to the title screen if they aren't already there, allowing the player to clear a save slot if needed, this node also has an artificial delay that can be changed if needed
| Finished | Autosaving | Node Name: Autosave | This code will automatically save the game data, to be used before important event so that if the player fails or crashes, they aren't set back too far. This node takes into account the player's deltaseconds and the developer-input timer to add in a small pause that lets the player no, thanks to a UI, that the game is autosaving.
| Finished | Quick Time Events | Node Name: Start QTE / UI_QTE | SO much shit I'm not even going to describe it here lol, still needs to be tested and bug-fixed a bit probably tho idk
| Finished | Sound Handler | BP_AudioPoint | Level Design Toolkit: Something to add in noises to the game, I'll add the ability for it to either be a loop, triggered by a location box, or to just play at the beginning of a scene, can be used for either SFX or Music
| Finished | UI Handler | BP_UIPoint | Level Design Toolkit: A blueprint to add in UI to the scene, can either be set to show up by default when entering the scene or instead when interacted with or clicked
| Finished | Title Functionality | UI_Title | Code in begin game functionality, animations, and camera movement setup for the title screen
| Finished | Interpolation Object | BP_InterpPoint | Level Design Toolkit: A blueprint that allows the level designer to select and object, set it to a certain point, and then interpolate that object between that set position and another selected position without needing to touch any blueprints, should only be used for basic movements, any advanced animation should use a specified blueprint
| Finished | Basic Movement Section | Node Name: Swap Scene Type | A node that'll take an existing object in the game, and then utilize the fade ui to seemlessly switch from a scene in which you're only watching, to a playable section with limited movement for the player to do certain actions
| In Progress | Github Site | N/A | Github Site
| Finished | Internal Data Saving | Node Name: Internal Save/Pull | Save node that'll save or pull certain data from an unwipeable save file inside of the game to be used for remembering certain choices across saves and changing the title screens after reaching certain points regardless of if the player restarts their game / save or not
| Finished | Advanced Music Player | BPI_MusicHandler | Complex music player that'll allow for music to be stopped and started, crossfaded, and much more to get developers much more freedom when it comes to weaving music into levels and scenes
| Finished | Freeroam Movement | Node Name: Begin Freeroam | A node that allows developers to switch from a regular scene to one in which the player has complete control of the movement of the character and can interact with the background and area around them
| Finished | Screen Shakeing | Node Name: Shake Event | A node that'll allow developers to call of a shake effect to simulate something slamming into something else, an earthquake, or any other similar effect
| Finished | QTE Endstate | UI_Death | A UI that can be slowly brought up to recognize and endstate after dying or failing a qte, it should temporarily slow down any game movement before then freezing all of it and bringing up the game over screen
| Finished | Button Spam QTE | Node Name: Setup Spam QTE | A quick time event that'll require the player to spam a button a set amount of times, and if the player doesn't manage to spam it enough, it can lead to an end state, this'll have a customizable amount / resistance based on an integer and/or float value that can be controlled when the node is called
| Blocked | Moverment Animation Code | BPA_Movement | The animation blueprints responsible for handling animations of the player both in and out of playable sections
| Finished | Rich Pressence | Node Name: Presence Handler | Discord Rich Presence support, so when playing the game, discord will detect this and display unique info about the game, such as locations, icons, etc
| In Progress | Freeroam Interactivity | BP_Interaction(1)(2)(etc) | Objects that the player will be able to interact with when in freeroam sections in the game, one that'll bring up dialogue, one that'll open something (ei a door or gate) and one that'll end the freeroam sections and begin the next scene of the game, with optional fade or not
| Finished | Notice UI | Node Name: Notice Event | A node that brings up a UI to let the player know that the current NPC noticed something about what just happened in the scene / their choice
| Finished | Multimesh Handler | BP_MultimeshHandler | A blueprint that can allow multiple meshes to be combined into a single model for use in the game up to 6 meshes at once.

## Models
MAIN ALR | MODELS: ALR
MODELING
| Must Have |  |  |  |  | Want |  |  |  |  | Wish
DO NOT EDIT: | Status | Models | Naming Convention | Information | Reference | Status | Models | Naming Convention | Information | Reference | Status | Models | Naming Convention | Information | Reference
Do not add/remove anything! | Finished | Basic Title Desert Terrain | M_Terrain | Not anything special, I just need some wide desert terrain, doesn't need to be super crazy or anything, mostly a flat plane
Please only change objective | Finished | Desert Rock Scene Pack | (Put here when u make it lol) | Need things like different types of rocks, empty bottles, dead weeds, etc!
status and nothing else! |  | El Puente Modular Pack | (Put here when u make it lol) | Just needs building outsides and a main center of town, u guys go crazy with it, also need the outside of a bar!
|  | El Puente Bar Modular Pack | (Put here when u make it lol) | Inside of the bar building, don't stress about it fiting with the outside modular pack, it can probably be in a seperate scene, go wild with it :salute:
|  | El Puente Welcome Sign | (Put here when u make it lol) | I'm imagining something smaller and more muted, but you guys can go with whatever style you want, just something to show off the name of the town as Carl walks in!
|  | El Puente Props | (Put here when u make it lol) | props such as fences, chairs, benches, crates, barrels, a centerpiece for the town, hitching posts, and lanturns. (feel free to add any other shit u come up with too)
|  | Tumbleweed Model | (Put here when u make it lol) | This'll be used in A LOT of places, it needs to look good
| Finished | Basic Terrain Pack | M_BTP | Just a basicaly terrain pack used to fill out some of the other terrains, all the edges being flat so I can be used in a modular way
| Finished | Introduction Canyon Terrain | M_Canyon | The canyon on the walk into El Cielo Muerto for the introduction section of the game before the player gets to El Puente, must be a complete model that can be viewed from most angles internally
| Finished | Empty Wagon | M_Wagon | A covered wagon model to be used in the intro canyon, el puente, and possibly in Terranova and other locations as well
| In Progress | Desert Clutter Pack | (U name it) | Old Fences, Broken Wheels, Cacti, Dead Bushes, Old Twigs, Joshua Trees Small Bushes
|  | Danny Cave Exterior | ^ | Exterior of the cave that can blend in well with the existing mountain range
|  | Danny Cave Interior | ^ | Interior of the cave, we should come up with a mockup together as a group
|  | Old Pass | ^ | The recently covered pass that used to connect El Puente to Terranova near Dead Man's Cavern
|  | Carl Snake Model / Walking animations | ^
^
^
^
^

## UI
MAIN ALR | INTERFACE: ALR
UI
| Must Have |  |  |  |  | Want |  |  |  |  | Wish
DO NOT EDIT: | Status | UI | Naming Convention | Information | Reference | Status | UI | Naming Convention | Information | Reference | Status | UI | Naming Convention | Information | Reference
For UI: | Finished | Dialogue UI | UI_Dialogue | dialogue ui lol | ( Still need to look for ui refs hol on )
Red = IMPORTANT | Finished | Choices UI | UI_Dialogue | This UI will be a in the same UI widget as the main dialogue box for better selection interaction | ( still gotta look for these 2 lol)
Do red first lmfaoo | Finished | Title UI | UI_Title | UI FOR TITLE SCREEN | ( need to descide still lol )
|  | Save Slot UI | UI_Saving | I'm going to use this same UI for the loading page too don't worry lol | https://www.reddit.com/media?url=https%3A%2F%2Fpreview.redd.it%2Ffile-softlocked-in-black-void-due-to-bug-v0-6c484dtpekne1.jpg%3Fwidth%3D1080%26crop%3Dsmart%26auto%3Dwebp%26s%3D464ff43c8e532a3e7fd476df9249248f2237f309
| Blocked | Settings UI | UI_Settings | NGL mostly gonna be an empty outline and I'll add in all the settings stuff when making the UI function | https://theinnergamer.net/wp-content/uploads/2017/03/clementine-walking-dead.jpg
| Finished | Autosave UI | UI_Autosave | Spinning logo in the bottom left corner of the screen to show the player that the game is autosaving
| Finished | Stress UI Effect | UI_QTE | A stress / red outline around the end of the screen that will grow darker the closser to the end of the quick time event the player is | https://www.reddit.com/media?url=https%3A%2F%2Fpreview.redd.it%2Fthe-most-frustrating-qte-in-season-1-v0-ackbi5v8myqc1.png%3Fwidth%3D640%26crop%3Dsmart%26auto%3Dwebp%26s%3D0aeeb73c4f1917f8b7f92a45984aa0deb777f719
| Finished | Notice UI | UI_Notice | Basically a little icon to pop up at the top of the screen that'll feature alongside text to let the player know that their choice will have an impact on the overrall story of the game and is being saved | https://miro.medium.com/v2/resize:fit:1400/1*dJZdieCw7FuNEw4lZw8oNQ.jpeg
| Finished | QTE UI | UI_QTE | Little icons to pop up during quick time events to show you the button that you need to press, need ones for all of the following buttons, they should all look the same but say the corrosponding buttons: W, A, S, D, Up, Left, Right, Down, Space, Q, E, F, X | https://i.redd.it/5ueaz72thnya1.png
| Finished | Title Button UI | UI_Title | Yony u alr know gng
|  | Interactions UI | UI_HUD | Need art for a cursor, Chat Icon, Fist Icon, Eye Icon, Hand Icon, Gun Icon, Coin Icon, Foot Icon, Card Icon, and Drink Icon, should be mostly white icons, the icons will be listed below the cursor, the cursor should look interesting but I'm leaving the details up to you, but I think maybe a gun crosshair could be cool, but really whatever you think would look good | https://youtu.be/-U8Tu9MkEb4?t=14039

## Sounds
MAIN ALR | SFX/MUSIC: ALR
Sound
| Must Have |  |  |  |  | Want |  |  |  |  | Wish
DO NOT EDIT: | Status | Sound | Naming Convention | Information | Reference | Status | Sound | Naming Convention | Information | Reference | Status | Sound | Naming Convention | Information | Reference
Do not add/remove anything! | Finished | Wind Sound | sfx_wind | Just typical wind noises, but try to get this free online but also might go out and record it myself if I can find a place I like the sound of! I'm alr doing this one lol, -Cai
Please only change objective |  | Water Dropping Sound | sfx_drop | Just a water dropping noise, for caves
status and nothing else! |  | Carl's Text Typing Sound | sfx_carltalk | need 2 noises that can be alternated between to form Carl's text noises for when his dialogue is being typed out
|  | Basic Male Typing Sound | sfx_basictalk1 | 2 basic deep noises to serve as most text typing sounds for generic npcs and the like
|  | Basic Female Typing Sound | sfx_basictalk2 | 2 basic lighter noises that can be alternated between the form the typing noises for basic female characters in the game