## Coding
MainALR | CODING: ALR
Coding
| Must Have |  |  |  | Want |  |  |  | Wish
DO NOT EDIT: | Status | Code | Naming Convention | Information | Status | Code | Naming Convention | Information | Status | Code | Naming Convention | Information
Do not add/remove anything! | Finished | Camera System | Node Name: Change Scene | To use the change scene node to switch to another camera, to get a location, set up the BP_CameraLocator in the right direction/location, then get the transform data and input it into a new row in the D_Scene data table, be sure to name the table and input the number correctly into the node, for node settings, input the row number and then have the dropdown on Non-Level-Fade for changing scenes inside of a level, and then Transparent to Black if you're changing into a new level (DO NOT PUT IT ON BLACK TO TRANSPARENT!!!!) If you're putting it on Transparent to Black, make sure to set the new level's name in the Data Table (D_Scenes)
Please only change objective | Finished | Scene Starter | BP_SceneStarter | Level Design Toolkit: This object is put in the level to let the handler know which camera it is supposed to start with and what scene it is supposed to play first. Make sure to NOT TOUCH THE FADE FOR THIS, DO NOT.
status and nothing else! | Finished | Dialogue Backend | Node Name: Start/Run/End Dialogue | These 3 nodes can be used to enter/bring up the ui, start a dialogue scrolling by grabbing a certain dialogue row from the data table, and the nending dialogue
| Finished | Cinematic Camera System | Node Name: Sweep Scene | To use the sweep scene node to sweep the camera between two locations, put in the first, and current location, in the Scene #1 Slot. It is very important that the camera is already at the first location you input. Next you input the desired location to interpolate to in the Scene #2 Slot, you'll have to tinker a little bit with the speed and rotate value, the rotate value should probably be VERY low though, the default values are about what is good for most cases.
| Blocked | Title Card Popup | UI_Popup | ( TITLE NEEDS TO BE DONE FIRST ) Going to have a popup during in the intro section with a panning camera, this might require some outside UI Design, but honestly it should be something that I can mostly just do inside of Unreal
| Finished | Saving Player Data | Node Name: Save Data | This node saves all of the player data needed to start the game back where the player left off, the listed duration counter adds a artificial delay to the save
| Finished | Grabbing Player Data | Node Name: Grab Data | This node loads in all critical save data needed for the player to noad their saved game, the direction add a artificial delay to the load depending on what is needed in each situation
| Finished | Wipe Player Data | Node Name: Wipe Data | This node wipes all of the player's data and returns them to the title screen if they aren't already there, allowing the player to clear a save slot if needed, this node also has an artificial delay that can be changed if needed
| Finished | Autosaving | Node Name: Autosave | This code will automatically save the game data, to be used before important event so that if the player fails or crashes, they aren't set back too far. This node takes into account the player's deltaseconds and the developer-input timer to add in a small pause that lets the player no, thanks to a UI, that the game is autosaving.
| Finished | Quick Time Events | Node Name: Start QTE / UI_QTE | SO much shit I'm not even going to describe it here lol, still needs to be tested and bug-fixed a bit probably tho idk
| Finished | Sound Handler | BP_AudioPoint | Level Design Toolkit: Something to add in noises to the game, I'll add the ability for it to either be a loop, triggered by a location box, or to just play at the beginning of a scene, can be used for either SFX or Music
| Finished | UI Handler | BP_UIPoint | Level Design Toolkit: A blueprint to add in UI to the scene, can either be set to show up by default when entering the scene or instead when interacted with or clicked
| In Progress | Title Functionality | UI_Title | Code in begin game functionality, animations, and camera movement setup for the title screen

## Models
MAIN ALR | MODELS: ALR
MODELING
| Must Have |  |  |  |  | Want |  |  |  |  | Wish
DO NOT EDIT: | Status | Models | Naming Convention | Information | Reference | Status | Models | Naming Convention | Information | Reference | Status | Models | Naming Convention | Information | Reference
Do not add/remove anything! | Finished | Basic Title Desert Terrain | M_Terrain | Not anything special, I just need some wide desert terrain, doesn't need to be super crazy or anything, mostly a flat plane
Please only change objective | In Progress | Desert Rock Scene Pack | (Put here when u make it lol) | Need things like different types of rocks, empty bottles, dead weeds, etc!
status and nothing else! |  | El Puente Modular Pack | (Put here when u make it lol) | Just needs building outsides and a main center of town, u guys go crazy with it, also need the outside of a bar!
|  | El Puente Bar Modular Pack | (Put here when u make it lol) | Inside of the bar building, don't stress about it fiting with the outside modular pack, it can probably be in a seperate scene, go wild with it :salute:
|  | El Puente Welcome Sign | (Put here when u make it lol) | I'm imagining something smaller and more muted, but you guys can go with whatever style you want, just something to show off the name of the town as Carl walks in!
|  | El Puente Rocky Terrain | (Put here when u make it lol) | terrain bro, mostly flat for the town
|  | Tumbleweed Model | (Put here when u make it lol) | This'll be used in A LOT of places, it needs to look good
| Finished | Basic Terrain Pack | M_BTP | Just a basicaly terrain pack used to fill out some of the other terrains, all the edges being flat so I can be used in a modular way

## UI
MAIN ALR | INTERFACE: ALR
UI
| Must Have |  |  |  |  | Want |  |  |  |  | Wish
DO NOT EDIT: | Status | UI | Naming Convention | Information | Reference | Status | UI | Naming Convention | Information | Reference | Status | UI | Naming Convention | Information | Reference
For UI: | In Progress | Dialogue UI | UI_Dialogue | dialogue ui lol | ( Still need to look for ui refs hol on )
Red = IMPORTANT |  | Choices UI | UI_Dialogue | This UI will be a in the same UI widget as the main dialogue box for better selection interaction | ( still gotta look for these 2 lol)
Do red first lmfaoo |  | Title UI | UI_Title | UI FOR TITLE SCREEN | ( need to descide still lol )
|  | Save Slot UI | UI_Saving | I'm going to use this same UI for the loading page too don't worry lol | https://www.reddit.com/media?url=https%3A%2F%2Fpreview.redd.it%2Ffile-softlocked-in-black-void-due-to-bug-v0-6c484dtpekne1.jpg%3Fwidth%3D1080%26crop%3Dsmart%26auto%3Dwebp%26s%3D464ff43c8e532a3e7fd476df9249248f2237f309
|  | Settings UI | UI_Settings | NGL mostly gonna be an empty outline and I'll add in all the settings stuff when making the UI function | idk
|  | Autosave UI | UI_Autosave | Spinning logo in the bottom left corner of the screen to show the player that the game is autosaving
|  | Stress UI Effect | UI_QTE | A stress / red outline around the end of the screen that will grow darker the closser to the end of the quick time event the player is | https://www.reddit.com/media?url=https%3A%2F%2Fpreview.redd.it%2Fthe-most-frustrating-qte-in-season-1-v0-ackbi5v8myqc1.png%3Fwidth%3D640%26crop%3Dsmart%26auto%3Dwebp%26s%3D0aeeb73c4f1917f8b7f92a45984aa0deb777f719
|  | Notice UI | UI_Notice | Basically a little icon to pop up at the top of the screen that'll feature alongside text to let the player know that their choice will have an impact on the overrall story of the game and is being saved | https://miro.medium.com/v2/resize:fit:1400/1*dJZdieCw7FuNEw4lZw8oNQ.jpeg
|  | QTE UI | UI_QTE | Little icons to pop up during quick time events to show you the button that you need to press, need ones for all of the following buttons, they should all look the same but say the corrosponding buttons: W, A, S, D, Up, Left, Right, Down, Space, Q, E, F, X | https://i.redd.it/5ueaz72thnya1.png

## Sounds
MAIN ALR | SFX/MUSIC: ALR
Sound
| Must Have |  |  |  |  | Want |  |  |  |  | Wish
DO NOT EDIT: | Status | Sound | Naming Convention | Information | Reference | Status | Sound | Naming Convention | Information | Reference | Status | Sound | Naming Convention | Information | Reference
Do not add/remove anything! | Finished | Wind Sound | sfx_wind | Just typical wind noises, but try to get this free online but also might go out and record it myself if I can find a place I like the sound of! I'm alr doing this one lol, -Cai
Please only change objective |  | Water Dropping Sound | sfx_drop | Just a water dropping noise, for caves
status and nothing else!